## Sheet1
SAMPLE - ANNUAL FUND CAMPAIGN CALENDAR
January | February | March | April | May | June | July | August | September | October | November | December
START Step 1. Your Fundraising Team | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet) | Step 1. (continue to meet)
Meet with your Fundraising Development
Committee. Create one if you do not have
one in place.
START Step 2. Annual Funding Campaign Calendar | Step 2. (continue) | END Step 2. (Have completed calendar by Mid-March) | Implement Actions on calendar | Implement Actions on calendar | Implement Actions on calendar | Implement Actions on calendar | Implement Actions on calendar | Implement Actions on calendar | Implement Actions on calendar | Implement Actions on calendar | Implement Actions on calendar
Set up a calendar by going to Dashboard,
Tools, and click on Calendar. Create a yearly
calender. Suggested name: Annual Campaign (year)
START Step 3. Campaign Purpose and Goal(s) | END Step 3. (Have goal(s) of campaign by end of February)
START Step 4. Establish Campaign Goal Amount | Step 4. (continue) | END Step 4. (Have Campaign Goal Amount by the end
of March)
| START Step 5. Create Your Campaign Budget | END Step 5. (Have a Campaign Budget by Mid-March)
| START Step 6. Segment Your Donors | END Step 6. (Have segmentation completed to include
in Marketing Plan)
| START Step 7. Create Your Marketing and Events Plan | STEP 7. (continue) | END Step 7. (Have Marketing Plan | STEP 7. Implement Actions | STEP 7. Implement Actions | STEP 7. Implement Actions | STEP 7. Implement Actions | STEP 7. Implement Actions | STEP 7. Implement Actions | STEP 7. Implement Actions | STEP 7. Implement Actions
by mid- April)
|  | START Step 8. Create Your Stewardship Plan | STEP 8. (Have completed by end of the month) | STEP 8. Implement Actions | STEP 8. Implement Actions | STEP 8. Implement Actions | STEP 8. Implement Actions | STEP 8. Implement Actions | STEP 8. Implement Actions | STEP 8. Implement Actions | STEP 8. Implement Actions
|  | START Step 9. Create Your Cultivation Plan | Step 9. (continue) | END Step 9. (have plan by end of May) | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions
|  |  | START Step 10. Create your Solicitation Plan | STEP. 10 (continue) | END Step 10. (have plan by end of June) | STEP 10. Implement Actions | STEP 10. Implement Actions | STEP 10. Implement Actions | STEP 10. Implement Actions | STEP 10. Implement Actions | STEP 10. Implement Actions
|  |  | START Step 11. Start Volunteers | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | STEP 9. Implement Actions | END Step 11. (By end of the month)
[8 empty] | START Step 12. ASK | STEP 12 (continue) | STEP 12 (continue) | END Step 12. (By end of the month)
[10 empty] | START Step 13. Keep Track | Step 13. (May continue into the
[10 empty] | When you are at approximately | next month)
90 percent of goal, start looking back
at how your campaign went, assess if
your stewardship plan succeeded